## Work Plan
GANTT ŞEMASI
PROJE YÖNETİCİSİ | Doctor Instructor Halit ERGEZER
TASK DEFINITION | Status | START DATE | FINISH DATE | TAMAMLANMA YÜZDESİ | Ekim-Kasım-Aralık | Ekim |  |  |  | Kasım |  |  |  | Aralık |  |  |  | Ocak
[6 empty] | Hafta |  |  |  | Hafta |  |  |  | Hafta |  |  |  | Hafta
[6 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
DOCUMENTS | In progress | 2021-10-26 | 2022-10-25 | 100%
Project Proposal Form | Complete | 2021-10-23 | 2021-11-05 | 100% | bar: Hafta 3 to Hafta 1
Project Selection Form | Complete | 2021-10-24 | 2021-11-05 | 100% | bar: Hafta 3 to Hafta 1
GitHub Repository | Complete | 2021-10-28 | 2021-11-05 | 100% | bar: Hafta 1
Project Work Plan | Complete | 2021-11-07 | 2021-11-12 | 100% | bar: Hafta 1
Literature Review | Complete | 2021-10-25 | 2021-11-12 | 25% | bar: Hafta 3 to Hafta 1
Software Requirements Specification (SRS) | In progress | 2021-11-12 | 2021-12-10 | 25% | bar: Hafta 2 to Hafta 2
Project Webpage | Not started | 2021-12-11 | 2021-12-17 | bar: Hafta 1 to Hafta 3
Software Design Description (SDD) | Not started | 2021-12-18 | 2021-12-31 | bar: Hafta 3 to Hafta 4
Project Report / Project Tracking Form | Not started | 2022-01-01 | 2022-01-07 | bar: Hafta 1
Presentation | Not started | 2022-01-05 | 2022-01-23 | bar: Hafta 1 to Hafta 4